## Hoja1
Budget
Personnel: | Year | Montly | Change Request | Number of people | New Personnel | Months work | Montly | Year | Salary for change request | Total | Percentage
Project Manager | 87300 | 7275 | CR 4 | 2 | Web Designer | 1 | 7500 | 90000 | 15000 | 21500 | 3.56
Finance advisor | 79908 | 6659 |  | 1 | Graphic Designer | 1 | 6500 | 78000 | 6500
Legal adviser | 102648 | 8554 | CR 3 | 2 | Software Engineer | 8 | 9500 | 114000 | 152000 | 220000 | 36.42
Senior developer | 120912 | 10076 |  | 1 | Sound Engineer | 8 | 8500 | 102000 | 68000
Semi senior developer | 103968 | 8664 | CR 2 | 1 | Team | 1.5 | 31665 | 379980 | 47497.5 | 47497.5 | 7.86
Junior developer | 67800 | 5650
Office and Services | Year | Monthly | CR 1 | 1 | Team | 2 | 31665 | 379980 | 63330 | 63330 | 10.48
Office rent | 37776 | 3148
Services (water, internet, electricity) | 3708 | 309
Total (Team devoloper and Project Manager) | 379980 | 31665 | Time |  |  |  |  | Human Resources
Total (Personal legal and finance) | 182556 | 15213 | Change Request | Origin Time (Months) | New Time (Months) | Percentage |  | Change Request | New Members | Team Members (Original Team) | Percentaje
Total (Services and Office) | 41484 | 3457 | CR1 | 12 | 2 | 16.67 |  | CR1 | 0 | 7 | 0
Total (Personal, Office, Services) | 604020 | 50335 | CR2 | 12 | 1.5 | 12.5 |  | CR2 | 0 | 7 | 0
Total of the project | 604020 |  | CR3 | 12 | 8 | 66.67 |  | CR3 | 3 | 7 | 42.86
|  |  | CR4 | 12 | 1 | 8.33 |  | CR4 | 3 | 7 | 42.86
|  |  | Change Request | Budget | Time | Human Resource | Effort | Potential Risk | Law Mandatory | First Approval | Ranking | Final Decision
|  |  | CR1 | Accepted | Accepted | Accepted | 13.58 | Medium | NO | Accepted | 3 | Accepted
|  |  | CR2 | Accepted | Accepted | Accepted | 10.18 | Medium | NO | Accepted | 2 | Accepted
|  |  | CR3 | Rejected | Rejected | Rejected | 51.55 | High | NO | Rejected | 4 | Rejected
|  |  | CR4 | Accepted | Accepted | Accepted | 5.95 | Low | NO | Accepted | 1 | Accepted